## Planner
Fiscal Quarter | [23 empty] | FY2027 Q2 | [63 empty] | FY2027 Q3
PI | [23 empty] | PI 1 | [49 empty] | PI 2 | [49 empty] | PI 3
Sprint | [23 empty] | Sprint 1 | [9 empty] | Sprint 2 | [9 empty] | Sprint 3 | [9 empty] | Sprint 4 | [9 empty] | Sprint 5 | [9 empty] | Sprint 6 | [9 empty] | Sprint 7 | [9 empty] | Sprint 8 | [9 empty] | Sprint 9 | [9 empty] | Sprint 10 | [9 empty] | Sprint 11 | [9 empty] | Sprint 12 | [9 empty] | Sprint 13
Month | [23 empty] | Jan 2026 | [21 empty] | Feb 2026 | [19 empty] | Mar 2026 | [21 empty] | Apr 2026 | [21 empty] | May 2026 | [20 empty] | Jun 2026
Week Number | [23 empty] | Week 1 |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12 |  |  |  |  | Week 13 |  |  |  |  | Week 14 |  |  |  |  | Week 15 |  |  |  |  | Week 16 |  |  |  |  | Week 17 |  |  |  |  | Week 18 |  |  |  |  | Week 19 |  |  |  |  | Week 20 |  |  |  |  | Week 21 |  |  |  |  | Week 22 |  |  |  |  | Week 23 |  |  |  |  | Week 24 |  |  |  |  | Week 25 |  |  |  |  | Week 26 |  |  |  |  | Week 27
Date | [23 empty] | 🇺🇸 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 🇺🇸 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 🇺🇸 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 31 | 1 | 2 | 🇨🇦 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 🇨🇦 | 19 | 20 | 21 | 22 | 🇺🇸 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 🇺🇸 | 22 | 23 | 24 | 25 | 26 | 29 | 30
DoW | [23 empty] | 🇺🇸 | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | 🇺🇸 | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | 🇺🇸 | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | 🇨🇦 | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | 🇨🇦 | Tue | Wed | Thu | Fri | 🇺🇸 | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | 🇺🇸 | Mon | Tue | Wed | Thu | Fri | Mon | Tue
id | status | priority | wbs | rollup | milestone | percent_complete | name | effort | duration | start_date | end_date | earliest_start_date | latest_start_date | earliest_end_date | latest_end_date | predecessors | resource_names | resource_group | notes | icon | color | tags
100 | active | 0 | NP.1 | 1 | 0 | 0 | Discovery & Requirements |  |  | 20260202 | 20260227 | [7 empty] | Requirements elicitation and scoping phase |  |  | Discovery
112 | active | 2 | NP.1.4 | 0 | 0 | 0 | Legacy System Audit |  |  | 20260202 | 20260220 | [6 empty] | Backend | Catalog current services and data flows | analysis | skyblue | Discovery | bar: Mon to Fri
99 | active | 0 | NP | 1 | 0 | 0 | NimbusPay Modernization |  |  | 20260202 | 20260731 | [7 empty] | Full program rollup spanning discovery through production rollout |  |  |  | ▶
108 | active | 0 | NP.1 | 0 | 1 | 0 | Project Kickoff |  |  | 20260202 | 20260202 | [6 empty] | Product | All-hands kickoff and charter walkthrough | calendar | skyblue | Discovery |  | Mon: calendar
109 | active | 1 | NP.1.1 | 0 | 0 | 0 | Stakeholder Interviews |  |  | 20260202 | 20260213 | [6 empty] | Product | Discovery sessions with finance, ops, and support leaders | group | skyblue | Discovery | bar: Mon to Fri
110 | active | 1 | NP.1.2 | 0 | 0 | 0 | Business Requirements Workshop |  |  | 20260209 | 20260213 | [6 empty] | Product | Capture and prioritize functional requirements | presentation | skyblue | Discovery | bar: Mon to Fri
111 | active | 1 | NP.1.3 | 0 | 0 | 0 | Regulatory Compliance Review |  |  | 20260209 | 20260220 | [6 empty] | Security | PCI DSS and SOC2 scope assessment | shield | skyblue | Discovery | bar: Mon to Fri
113 | active | 2 | NP.1.5 | 0 | 0 | 0 | User Research Sessions |  |  | 20260209 | 20260220 | [6 empty] | UX | Contextual inquiries with merchant operators | heart | skyblue | Discovery | bar: Mon to Fri
114 | active | 2 | NP.1.6 | 0 | 0 | 0 | Non-functional Requirements Draft |  |  | 20260216 | 20260227 | [6 empty] | Backend | Throughput, latency, and availability targets | ruler | skyblue | Discovery | bar: 🇺🇸 to Fri
101 | active | 0 | NP.2 | 1 | 0 | 0 | Architecture & Design |  |  | 20260223 | 20260313 | [7 empty] | System, API, data, and UX design |  |  | Design
116 | active | 1 | NP.2.1 | 0 | 0 | 0 | Architecture Vision Workshop |  |  | 20260223 | 20260227 | [6 empty] | Backend | Set north-star architecture and constraints | lightbulb | steelblue | Design | bar: Mon to Fri
117 | active | 1 | NP.2.2 | 0 | 0 | 0 | System Architecture Spec |  |  | 20260223 | 20260306 | [6 empty] | Backend | Service decomposition and runtime topology | ruler | steelblue | Design | bar: Mon to Fri
115 | active | 0 | NP.1 | 0 | 1 | 0 | Requirements Sign-off |  |  | 20260227 | 20260227 | [6 empty] | Product | Steering committee approves requirements baseline | check | skyblue | Discovery |  | Fri: check
118 | active | 2 | NP.2.3 | 0 | 0 | 0 | API Contract Design |  |  | 20260302 | 20260313 | [6 empty] | Backend | OpenAPI specs for payments and identity surfaces | code | steelblue | Design | bar: Mon to Fri
119 | active | 2 | NP.2.4 | 0 | 0 | 0 | Data Model Design |  |  | 20260302 | 20260313 | [6 empty] | Backend | Ledger schema and event sourcing patterns | database | steelblue | Design | bar: Mon to Fri
122 | active | 1 | NP.2.7 | 0 | 0 | 0 | Security Threat Model |  |  | 20260302 | 20260313 | [6 empty] | Security | STRIDE analysis on new attack surface | shield | steelblue | Design | bar: Mon to Fri
120 | active | 2 | NP.2.5 | 0 | 0 | 0 | UX Wireframes |  |  | 20260302 | 20260313 | [6 empty] | UX | Low-fidelity flows for primary personas | pencil | steelblue | Design | bar: Mon to Fri
121 | active | 2 | NP.2.6 | 0 | 0 | 0 | Visual Design System |  |  | 20260309 | 20260313 | [6 empty] | UX | Component library and tokens | presentation | steelblue | Design | bar: Mon to Fri
123 | active | 1 | NP.2 | 0 | 1 | 0 | Architecture Review Board |  |  | 20260313 | 20260313 | [6 empty] | Backend | Cross-team review and approval | star | steelblue | Design |  | Fri: star
126 | active | 2 | NP.3.S1.2 | 0 | 0 | 0 | Auth Web Implementation |  |  | 20260316 | 20260403 | [6 empty] | Frontend | Sign-in, MFA, and account recovery screens | laptop | seagreen | Sprint1 | bar: Mon to 🇨🇦
128 | active | 1 | NP.3.S1.4 | 0 | 0 | 0 | CI/CD Pipeline Setup |  |  | 20260316 | 20260327 | [6 empty] | DevOps | Build, test, and artifact promotion stages | tools | seagreen | Sprint1 | bar: Mon to Fri
102 | active | 0 | NP.3 | 1 | 0 | 0 | Development Sprints |  |  | 20260316 | 20260605 | [7 empty] | Four iterative build sprints |  |  | Build
125 | active | 1 | NP.3.S1.1 | 0 | 0 | 0 | Identity Service Build |  |  | 20260316 | 20260403 | [6 empty] | Backend | OIDC issuer, user store, and token service | code | seagreen | Sprint1 | bar: Mon to 🇨🇦
127 | active | 2 | NP.3.S1.3 | 0 | 0 | 0 | Mobile Auth Module |  |  | 20260316 | 20260403 | [6 empty] | Mobile | iOS and Android biometric login | phone | seagreen | Sprint1 | bar: Mon to 🇨🇦
103 | active | 0 | NP.4 | 1 | 0 | 0 | QA & Testing |  |  | 20260316 | 20260619 | [7 empty] | Verification, validation, and quality gates |  |  | Verify
154 | active | 2 | NP.4.1 | 0 | 0 | 0 | QA Test Plan |  |  | 20260316 | 20260327 | [6 empty] | QA | Strategy, coverage matrix, and entry/exit criteria | clipboard | orange | Verify | bar: Mon to Fri
124 | active | 1 | NP.3.S1 | 0 | 1 | 0 | Sprint 1 Planning |  |  | 20260316 | 20260316 | [6 empty] | Product | Backlog refinement for auth and API foundation | calendar | seagreen | Sprint1 |  | Mon: calendar
155 | active | 2 | NP.4.2 | 0 | 0 | 0 | Unit Test Buildout |  |  | 20260330 | 20260501 | [6 empty] | QA | Component-level coverage with mocks | check | orange | Verify | bar: Mon to Fri
129 | active | 2 | NP.3.S1 | 0 | 0 | 0 | Sprint 1 Demo |  |  | 20260403 | 20260403 | [6 empty] | Product | Stakeholder demo of authentication flow | presenter | seagreen | Sprint1 |  | 🇨🇦: presenter
130 | active | 1 | NP.3.S1 | 0 | 1 | 0 | Sprint 1 Review |  |  | 20260403 | 20260403 | [6 empty] | Product | Sprint outcomes accepted | flag | seagreen | Sprint1 |  | 🇨🇦: flag
134 | active | 2 | NP.3.S2.3 | 0 | 0 | 0 | Account Management UI |  |  | 20260406 | 20260424 | [6 empty] | Frontend | Merchant dashboard for accounts and balances | laptop | mediumseagreen | Sprint2 | bar: Mon to Fri
156 | active | 2 | NP.4.3 | 0 | 0 | 0 | Integration Test Buildout |  |  | 20260406 | 20260515 | [6 empty] | QA | Service-to-service contract tests | tools | orange | Verify | bar: Mon to Fri
136 | active | 2 | NP.3.S2.5 | 0 | 0 | 0 | Internal API Gateway |  |  | 20260406 | 20260417 | [6 empty] | DevOps | Routing, auth, and rate limiting | globe | mediumseagreen | Sprint2 | bar: Mon to Fri
133 | active | 1 | NP.3.S2.2 | 0 | 0 | 0 | Ledger Service Build |  |  | 20260406 | 20260424 | [6 empty] | Backend | Double-entry ledger with idempotent writes | database | mediumseagreen | Sprint2 | bar: Mon to Fri
135 | active | 2 | NP.3.S2.4 | 0 | 0 | 0 | Mobile Payments Flow |  |  | 20260406 | 20260424 | [6 empty] | Mobile | Tap-to-pay and receipt screens | phone | mediumseagreen | Sprint2 | bar: Mon to Fri
132 | active | 1 | NP.3.S2.1 | 0 | 0 | 0 | Payments Service Build |  |  | 20260406 | 20260424 | [6 empty] | Backend | Charge, refund, and dispute APIs | code | mediumseagreen | Sprint2 | bar: Mon to Fri
131 | active | 1 | NP.3.S2 | 0 | 1 | 0 | Sprint 2 Planning |  |  | 20260406 | 20260406 | [6 empty] | Product | Plan core features sprint | calendar | mediumseagreen | Sprint2 |  | Mon: calendar
137 | active | 2 | NP.3.S2 | 0 | 0 | 0 | Sprint 2 Demo |  |  | 20260424 | 20260424 | [6 empty] | Product | Demo of charge and ledger flows | presenter | mediumseagreen | Sprint2 |  | Fri: presenter
138 | active | 1 | NP.3.S2 | 0 | 1 | 0 | Sprint 2 Review |  |  | 20260424 | 20260424 | [6 empty] | Product | Sprint outcomes accepted | flag | mediumseagreen | Sprint2 |  | Fri: flag
140 | active | 1 | NP.3.S3.1 | 0 | 0 | 0 | Bank Partner Integration |  |  | 20260427 | 20260515 | [6 empty] | Backend | ACH and card-network connectors | globe | coral | Sprint3 | bar: Mon to Fri
143 | active | 2 | NP.3.S3.4 | 0 | 0 | 0 | Mobile Push Notifications |  |  | 20260427 | 20260508 | [6 empty] | Mobile | APNs and FCM wiring | phone | coral | Sprint3 | bar: Mon to Fri
141 | active | 2 | NP.3.S3.2 | 0 | 0 | 0 | Notification Service |  |  | 20260427 | 20260508 | [6 empty] | Backend | Email, SMS, and push fan-out | code | coral | Sprint3 | bar: Mon to Fri
144 | active | 2 | NP.3.S3.5 | 0 | 0 | 0 | Observability Stack |  |  | 20260427 | 20260515 | [6 empty] | DevOps | Logs, metrics, and tracing baseline | server | coral | Sprint3 | bar: Mon to Fri
142 | active | 2 | NP.3.S3.3 | 0 | 0 | 0 | Reporting Module |  |  | 20260427 | 20260515 | [6 empty] | Frontend | Settlement and reconciliation reports | analysis | coral | Sprint3 | bar: Mon to Fri
139 | active | 1 | NP.3.S3 | 0 | 1 | 0 | Sprint 3 Planning |  |  | 20260427 | 20260427 | [6 empty] | Product | Plan integration sprint | calendar | coral | Sprint3 |  | Mon: calendar
162 | active | 2 | NP.5.1 | 0 | 0 | 0 | Cloud Account Provisioning |  |  | 20260504 | 20260515 | [6 empty] | Ops | Production and DR accounts, IAM, and VPCs | cloud | slategray | Operate | bar: Mon to Fri
104 | active | 0 | NP.5 | 1 | 0 | 0 | Operations Readiness |  |  | 20260504 | 20260717 | [7 empty] | Infrastructure, monitoring, and runbooks for production |  |  | Operate | ▶
163 | active | 1 | NP.5.2 | 0 | 0 | 0 | Production Infrastructure Build |  |  | 20260504 | 20260529 | [6 empty] | Ops | Kubernetes clusters and managed data stores | server | slategray | Operate | bar: Mon to Fri
157 | active | 2 | NP.4.4 | 0 | 0 | 0 | Regression Test Suite |  |  | 20260504 | 20260529 | [6 empty] | QA | Automated regression scenarios | analysis | orange | Verify | bar: Mon to Fri
177 | active | 2 | NP.7.1 | 0 | 0 | 0 | Beta Cohort Recruitment |  |  | 20260511 | 20260522 | [6 empty] | Product | Identify and onboard pilot merchants | group | mediumpurple | UAT | bar: Mon to Fri
158 | active | 1 | NP.4.5 | 0 | 0 | 0 | Load & Performance Testing |  |  | 20260511 | 20260529 | [6 empty] | QA | Peak season traffic simulation | fire | orange | Verify | bar: Mon to Fri
106 | active | 0 | NP.7 | 1 | 0 | 0 | User Acceptance |  |  | 20260511 | 20260626 | [7 empty] | Beta program and stakeholder UAT cycles |  |  | UAT
145 | active | 2 | NP.3.S3 | 0 | 0 | 0 | Sprint 3 Demo |  |  | 20260515 | 20260515 | [6 empty] | Product | Integration demo | presenter | coral | Sprint3 |  | Fri: presenter
146 | active | 1 | NP.3.S3 | 0 | 1 | 0 | Sprint 3 Review |  |  | 20260515 | 20260515 | [6 empty] | Product | Sprint outcomes accepted | flag | coral | Sprint3 |  | Fri: flag
160 | active | 2 | NP.4.7 | 0 | 0 | 0 | Accessibility Audit |  |  | 20260518 | 20260529 | [6 empty] | UX | WCAG 2.2 AA conformance review | heart | orange | Verify | bar: 🇨🇦 to Fri
149 | active | 2 | NP.3.S4.2 | 0 | 0 | 0 | Frontend Polish |  |  | 20260518 | 20260605 | [6 empty] | Frontend | Accessibility, copy, and visual cleanup | pencil | gold | Sprint4 | bar: 🇨🇦 to Fri
150 | active | 2 | NP.3.S4.3 | 0 | 0 | 0 | Mobile Hardening |  |  | 20260518 | 20260605 | [6 empty] | Mobile | Crash fixes and offline behavior | wrench | gold | Sprint4 | bar: 🇨🇦 to Fri
164 | active | 1 | NP.5.3 | 0 | 0 | 0 | Monitoring & Alerting Setup |  |  | 20260518 | 20260612 | [6 empty] | Ops | Dashboards, SLOs, and pager routing | warning | slategray | Operate | bar: 🇨🇦 to Fri
148 | active | 1 | NP.3.S4.1 | 0 | 0 | 0 | Performance Tuning |  |  | 20260518 | 20260605 | [6 empty] | Backend | Hot-path profiling and query optimization | lightbulb | gold | Sprint4 | bar: 🇨🇦 to Fri
159 | active | 1 | NP.4.6 | 0 | 0 | 0 | Security Penetration Test |  |  | 20260518 | 20260605 | [6 empty] | Security | External vendor red-team engagement | shield | orange | Verify | bar: 🇨🇦 to Fri
147 | active | 1 | NP.3.S4 | 0 | 1 | 0 | Sprint 4 Planning |  |  | 20260518 | 20260518 | [6 empty] | Product | Plan hardening sprint | calendar | gold | Sprint4 |  | 🇨🇦: calendar
151 | active | 2 | NP.3.S4.4 | 0 | 0 | 0 | Bug Bash Week |  |  | 20260525 | 20260529 | [6 empty] | QA | Cross-team defect hunt | bug | gold | Sprint4 | bar: 🇺🇸 to Fri
178 | active | 1 | NP.7.2 | 0 | 0 | 0 | UAT Cycle 1 |  |  | 20260525 | 20260605 | [6 empty] | Stakeholders | Guided scenarios on staging environment | group | mediumpurple | UAT | bar: 🇺🇸 to Fri
170 | active | 2 | NP.6.1 | 0 | 0 | 0 | Change Management Plan |  |  | 20260601 | 20260612 | [6 empty] | Product | Impact analysis and adoption roadmap | clipboard | plum | Adopt | bar: Mon to Fri
171 | active | 2 | NP.6.2 | 0 | 0 | 0 | End-User Training Materials |  |  | 20260601 | 20260626 | [6 empty] | Training | Guides and recorded walkthroughs | book | plum | Adopt | bar: Mon to Fri
105 | active | 0 | NP.6 | 1 | 0 | 0 | Organizational Readiness |  |  | 20260601 | 20260717 | [7 empty] | Change management, training, and communications |  |  | Adopt | ▶
165 | active | 2 | NP.5.4 | 0 | 0 | 0 | Runbook Authoring |  |  | 20260601 | 20260626 | [6 empty] | Ops | Operational procedures for top scenarios | book | slategray | Operate | bar: Mon to Fri
179 | active | 2 | NP.7.3 | 0 | 0 | 0 | UAT Defect Triage |  |  | 20260601 | 20260612 | [6 empty] | Product | Prioritize and assign UAT-found defects | bug | mediumpurple | UAT | bar: Mon to Fri
152 | active | 0 | NP.3.S4 | 0 | 1 | 0 | Code Freeze |  |  | 20260605 | 20260605 | [6 empty] | Product | Only release-critical changes accepted | clock | gold | Sprint4 |  | Fri: clock
153 | active | 1 | NP.3.S4 | 0 | 1 | 0 | Sprint 4 Review |  |  | 20260605 | 20260605 | [6 empty] | Product | Sprint outcomes accepted | flag | gold | Sprint4 |  | Fri: flag
166 | active | 1 | NP.5.5 | 0 | 0 | 0 | Backup & DR Procedures |  |  | 20260608 | 20260626 | [6 empty] | Ops | RPO/RTO validation and failover drills | hourglass | slategray | Operate | bar: Mon to Fri
175 | active | 2 | NP.6.6 | 0 | 0 | 0 | Help Center Content |  |  | 20260608 | 20260710 | [6 empty] | Training | Knowledge base articles and FAQs | doc | plum | Adopt | ▶ | bar: Mon to Tue
173 | active | 2 | NP.6.4 | 0 | 0 | 0 | Stakeholder Comms Plan |  |  | 20260608 | 20260619 | [6 empty] | Product | Cross-org launch communications | presentation | plum | Adopt | bar: Mon to 🇺🇸
180 | active | 1 | NP.7.4 | 0 | 0 | 0 | UAT Cycle 2 |  |  | 20260615 | 20260626 | [6 empty] | Stakeholders | Re-validation of fixes from cycle 1 | group | mediumpurple | UAT | bar: Mon to Fri
161 | active | 0 | NP.4 | 0 | 1 | 0 | QA Sign-off |  |  | 20260619 | 20260619 | [6 empty] | QA | All quality gates met | check | orange | Verify |  | 🇺🇸: check
174 | active | 2 | NP.6.5 | 0 | 0 | 0 | Launch Comms Drafted |  |  | 20260622 | 20260703 | [6 empty] | Product | External announcements and customer emails | notes | plum | Adopt | ▶ | bar: Mon to Tue
167 | active | 2 | NP.5.6 | 0 | 0 | 0 | On-call Rotation Setup |  |  | 20260622 | 20260703 | [6 empty] | Ops | Schedules, escalation, and handoff process | clock | slategray | Operate | ▶ | bar: Mon to Tue
172 | active | 2 | NP.6.3 | 0 | 0 | 0 | Support Team Training |  |  | 20260622 | 20260710 | [6 empty] | Training | Workshops for tier 1 and tier 2 support | group | plum | Adopt | ▶ | bar: Mon to Tue
181 | active | 0 | NP.7 | 0 | 1 | 0 | UAT Sign-off |  |  | 20260626 | 20260626 | [6 empty] | Stakeholders | Business stakeholders accept the release | thumbsup | mediumpurple | UAT |  | Fri: thumbsup