| Column Name | Alternative Name | Description | Preferred Format | Example |
| --- | --- | --- | --- | --- |
| ID | GUID | Unique ID for the task. | Alphanumeric string | 143 |
| Name | TaskName | Name of the task. | Alphanumeric string | Ditch |
| WBS |  | A unique code (work breakdown structure) used to represent a task's position within the hierarchical structure of tasks. | Alphanumeric string separated by periods (.) | PROJ1.Act1.Task.143 |
| Priority |  | Indicates the level of importance assigned to a task | Alphanumeric string 1 highest, 99 lowest priority | 77 |
| Milestone |  | Indicates whether a task is a milestone. | True or False - can be 0 for false and 1 for true | False |
| Summary | Rollup | Indicates whether a task is a summary task | True or False - can be 0 for false and 1 for true | False |
| Critical |  | Indicates whether a task has room in the schedule to slip, or if it is on the critical path. | True or False - can be 0 for false and 1 for true | False |
| Start | StartDate | Date and time that a task is scheduled to begin. | YYYYMMDDTHHMM | 20260602T1230 |
| Finish | EndDate | The date and time that a task is scheduled to be completed. | YYYYMMDDTHHMM | 20260602T1630 |
| Duration |  | Total span of active working time for a task. Not to be confused with the effort required to complete this task. | Alphanumeric string | 4hr |
| Work | Effort | Total amount of work scheduled to be performed on a task by all assigned resources. | Alphanumeric string | 0.5d |
| EarlyStart | earliest_start_date | The earliest date that a task can begin, based on the early start dates of predecessor and successor tasks and other constraints. | YYYYMMDDTHHMM | 20260523T0800 |
| EarlyFinish | earliest_end_date | The earliest date that a task can finish, based on early finish dates of predecessor and successor tasks, other constraints | YYYYMMDDTHHMM | 20260523T1700 |
| LateStart | latest_start_date | The latest date that a task can start without delaying the finish of the project. | YYYYMMDDTHHMM | 20260603T0800 |
| LateFinish | latest_end_date | The latest date that a task can finish without delaying the finish of the project. | YYYYMMDDTHHMM | 20260603T1630 |
| ActualStart |  | Date and time that a task actually began. | YYYYMMDDTHHMM | 20260602T0800 |
| ActualFinish |  | Date and time that a task actually finished. | YYYYMMDDTHHMM | 20260602T1200 |
| Deadline |  | Date entered as a deadline for the task. | YYYYMMDDTHHMM | 20260630 |
| StartVariance |  | The difference between a task's baseline start date and its currently scheduled start date. | Alphanumeric string | -4h |
| FinishVariance |  | The amount of time that represents the difference between a task's baseline finish date and its current finish date. | Alphanumeric string | -4h |
| FixedCost |  | A task expense that is not associated with people performing the work – this may be the cost of a fixed price contract, capital acquisition, equipment rental or other non-labor fee. This is the summation of all costs related to this task. | Numeric | 250.00 |
| PercentComplete | percent_complete | The current status of a task, expressed as the percentage of the task's duration that has been completed. | Decimal number between 0 and 1.0 where 1 is 100% | 1.0 |
| PercentWorkComplete |  | The current status of a task, expressed as the percentage of the task's work / effort that has been completed. | Decimal number between 0 and 1.0 where 1 is 100% | 1.0 |
| Cost |  | The total scheduled, or projected, cost for the labor associated with the task. This should exclude any FixedCost items. This is the summation of all labor costs related to this task. | Numeric | 200.00 |
| Notes |  | Notes about the task. | Alphanumeric string | This is the ditch that must be placed 4’ from the road for drainage for the water tower. |
| Resources | resource_names | Names of people associated to this task | Alphanumeric string | Pete, Garcia |
| ResourceGroups | resource_groups | Department(s) associated to this task | Alphanumeric string | Facilities |
| Predecessors |  | Specifies the predecessor tasks | ID values or WBS values | 123 |
| Successors |  | Specifies the successor tasks | ID values or WBS values | 258 |
| Icon |  | Name of icon to be used in visualizations of this task | Alphanumeric string | shovel |
| Color |  | Name of the color to be used in visualizations for this task. | Alphanumeric string | Green |
| Tags |  | Strings associated with this task to be used for selection, filtering, and style rule definition | Alphanumeric string | Construction, Grounds |
| Custom1 |  | Custom field holding company / user specific value(s) related to this task to be used for selection, filtering, and style rule definition. | Alphanumeric string | Equipment: $250.00 |
| Custom2 |  | Custom field holding company / user specific value(s) related to this task to be used for selection, filtering, and style rule definition. | Alphanumeric string | Pete: $25/hr Garcia: $25/hr |
| Custom3 |  | Custom field holding company / user specific value(s) related to this task to be used for selection, filtering, and style rule definition. | Alphanumeric string | CoA: 99345B2026 |
| Custom4 |  | Custom field holding company / user specific value(s) related to this task to be used for selection, filtering, and style rule definition. | Alphanumeric string | Greenbriar Resorts |
| Custom5 |  | Custom field holding company / user specific value(s) related to this task to be used for selection, filtering, and style rule definition. | Alphanumeric string |  |

The only mandatory columns are: Start, Finish, and Name. All other columns are optional.

YYYYMMDDTHHMM example 20260704T12:30 for 7/4/26 12:30pm

WBS values should be unique across all projects. This can be done easily by including a Project ID as part of the WBS structure.

Resources and ResourceGroups can contain lists of people’s, department and/or company names that are related to tasks.

There are no length limits to custom fields, notes, and tags. Therefore, if there are additional fields that are used in the applications that generate the data simply concatenate the values from these fields to be able to select, filter, and style visualization data.

Cost and FixedCost are currency values that are related to labor and non-labor respectively.

You may want to use one or more custom fields to itemize the costs that were used to derive the FixedCost and Cost fields for each task.

The preferable file format is Microsoft Excel. This allows multiple entries separated by commas (,) and the use of special characters like / ‘ “ $ etc.

The names of icons and colors need to be those found in the database. The names are not case sensitive.  See the reference documents for the current list of recognized values. If the name entered is not found in the database a style_rule will define the icon and/or color. The color name will be applied to the icon and/or duration bars in visualizations.

Duration and Work are units of time, for example 4 hours, 0.5 days, or 240 minutes. Most project tools assume 8 hours equals 1 working day. It is recommended to use the same units for all tasks within a project.

PercentComplete and PercentWorkComplete are computed values by project management tools. These will change from one day to another as work is performed against tasks.

ActualStart and ActualFinish are values that are not estimated or projected but are historic values of when the work began and ended.

Predecessors and Successors define the dependency graph of the tasks that comprise the project. The values should be either the ID or the WBS entries – values that uniquely identify individual tasks that do not change over time. The dependency graph is used to govern the order of the work – in conjunction with the schedule start dates.

Deadline is the date that the task MUST be completed. This may be different than the Finish date. It is intended to be the last possible date that the task can be accomplished without significant impact (financial or legal) to the project.