## Events
ID | Name | WBS | Priority | Milestone | Summary | Critical | Start | Finish | Duration | Work | EarlyStart | EarlyFinish | LateStart | LateFinish | ActualStart | ActualFinish | Deadline | StartVariance | FinishVariance | FixedCost | PercentComplete | PercentWorkComplete | Cost | Notes | Resources | ResourceGroups | Predecessors | Successors | Icon | Color | Tags | Custom1 | Custom2 | Custom3 | Custom4 | Custom5
143 | Ditch | PROJ1.Act1.Task.143 | 77 | False | False | False | 20260602T1230 | 20260602T1630 | 4hr | 0.5d | 20260523T0800 | 20260523T1700 | 20260603T0800 | 20260603T1630 | 20260602T0800 | 20260602T1200 | 20260630 | -4h | -4h | 250.00 | 1.0 | 1.0 | 200.00 | This is the ditch that must be placed 4' from the road for drainage for the water tower. | Pete, Garcia | Facilities | 123 | 258 | shovel | Green | Construction, Grounds | Equipment: $250.00 | Pete: $25/hr Garcia: $25/hr | CoA: 99345B2026 | Greenbriar Resorts
144 | Pour Footings | PROJ1.Act1.Task.144 | 50 | False | False | True | 20260603T0800 | 20260604T1700 | 2d | 1.5d | [6 empty] | 20260705 |  |  | 1200.00 | 0.25 | 0.2 | 640.00 | Requires inspection sign-off before pour. | Garcia | Facilities | 143 | 145 | hammer | SteelBlue | Construction | Concrete: $1,200.00 | Garcia: $25/hr | CoA: 99345B2026 | Greenbriar Resorts
145 | Site Handover | PROJ1.Act1.Task.145 | 10 | True | False | True | 20260605T1600 | 20260605T1600 | [12 empty] | 0 | 0 |  | Milestone: client walkthrough and key handover. | Pete | Facilities | 144 |  | flag | Gold | Construction, Milestone |  |  | CoA: 99345B2026 | Greenbriar Resorts
Note on A1: Unique ID for the task. Format: Alphanumeric string Also accepted: GUID Example: 143
Note on B1: Name of the task. Format: Alphanumeric string Also accepted: TaskName Example: Ditch REQUIRED
Note on C1: A unique code (work breakdown structure) used to represent a task's position within the hierarchical structure of tasks. Format: Alphanumeric string separated by periods (.) Example: PROJ1.Act1.Task.143
Note on D1: Indicates the level of importance assigned to a task. Format: Alphanumeric string. 1 highest, 99 lowest priority Example: 77
Note on E1: Indicates whether a task is a milestone. Format: True or False - can be 0 for false and 1 for true Example: False
Note on F1: Indicates whether a task is a summary task. Format: True or False - can be 0 for false and 1 for true Also accepted: Rollup Example: False
Note on G1: Indicates whether a task has room in the schedule to slip, or if it is on the critical path. Format: True or False - can be 0 for false and 1 for true Example: False
Note on H1: Date and time that a task is scheduled to begin. Format: YYYYMMDDTHHMM Also accepted: StartDate Example: 20260602T1230 REQUIRED
Note on I1: The date and time that a task is scheduled to be completed. Format: YYYYMMDDTHHMM Also accepted: EndDate Example: 20260602T1630 REQUIRED
Note on J1: Total span of active working time for a task. Not to be confused with the effort required to complete this task. Format: Alphanumeric string Example: 4hr
Note on K1: Total amount of work scheduled to be performed on a task by all assigned resources. Format: Alphanumeric string Also accepted: Effort Example: 0.5d
Note on L1: The earliest date that a task can begin, based on the early start dates of predecessor and successor tasks and other constraints. Format: YYYYMMDDTHHMM Also accepted: earliest_start_date Example: 20260523T0800
Note on M1: The earliest date that a task can finish, based on early finish dates of predecessor and successor tasks, other constraints. Format: YYYYMMDDTHHMM Also accepted: earliest_end_date Example: 20260523T1700
Note on N1: The latest date that a task can start without delaying the finish of the project. Format: YYYYMMDDTHHMM Also accepted: latest_start_date Example: 20260603T0800
Note on O1: The latest date that a task can finish without delaying the finish of the project. Format: YYYYMMDDTHHMM Also accepted: latest_end_date Example: 20260603T1630
Note on P1: Date and time that a task actually began. Format: YYYYMMDDTHHMM Example: 20260602T0800
Note on Q1: Date and time that a task actually finished. Format: YYYYMMDDTHHMM Example: 20260602T1200
Note on R1: Date entered as a deadline for the task. Format: YYYYMMDDTHHMM Example: 20260630
Note on S1: The difference between a task's baseline start date and its currently scheduled start date. Format: Alphanumeric string Example: -4h
Note on T1: The amount of time that represents the difference between a task's baseline finish date and its current finish date. Format: Alphanumeric string Example: -4h
Note on U1: A task expense that is not associated with people performing the work - this may be the cost of a fixed price contract, capital acquisition, equipment rental or other non-labor fee. This is the summation of all costs related to this task. Format: Numeric Example: 250.00
Note on V1: The current status of a task, expressed as the percentage of the task's duration that has been completed. Format: Decimal number between 0 and 1.0 where 1 is 100% Also accepted: percent_complete Example: 1.0
Note on W1: The current status of a task, expressed as the percentage of the task's work / effort that has been completed. Format: Decimal number between 0 and 1.0 where 1 is 100% Example: 1.0
Note on X1: The total scheduled, or projected, cost for the labor associated with the task. This should exclude any FixedCost items. This is the summation of all labor costs related to this task. Format: Numeric Example: 200.00
Note on Y1: Notes about the task. Format: Alphanumeric string Example: This is the ditch that must be placed 4' from the road for drainage for the water tower.
Note on Z1: Names of people associated to this task. Format: Alphanumeric string Also accepted: resource_names Example: Pete, Garcia
Note on AA1: Department(s) associated to this task. Format: Alphanumeric string Also accepted: resource_groups Example: Facilities
Note on AB1: Specifies the predecessor tasks. Format: ID values or WBS values Example: 123
Note on AC1: Specifies the successor tasks. Format: ID values or WBS values Example: 258
Note on AD1: Name of icon to be used in visualizations of this task. Format: Alphanumeric string Example: shovel
Note on AE1: Name of the color to be used in visualizations for this task. Format: Alphanumeric string Example: Green
Note on AF1: Strings associated with this task to be used for selection, filtering, and style rule definition. Format: Alphanumeric string Example: Construction, Grounds
Note on AG1: Custom field holding company / user specific value(s) related to this task to be used for selection, filtering, and style rule definition. Format: Alphanumeric string Example: Equipment: $250.00
Note on AH1: Custom field holding company / user specific value(s) related to this task to be used for selection, filtering, and style rule definition. Format: Alphanumeric string Example: Pete: $25/hr Garcia: $25/hr
Note on AI1: Custom field holding company / user specific value(s) related to this task to be used for selection, filtering, and style rule definition. Format: Alphanumeric string Example: CoA: 99345B2026
Note on AJ1: Custom field holding company / user specific value(s) related to this task to be used for selection, filtering, and style rule definition. Format: Alphanumeric string Example: Greenbriar Resorts
Note on AK1: Custom field holding company / user specific value(s) related to this task to be used for selection, filtering, and style rule definition. Format: Alphanumeric string

## Data Dictionary
Column Name | Alternative Name | Description | Preferred Format | Example
ID | GUID | Unique ID for the task. | Alphanumeric string | 143
Name | TaskName | Name of the task. | Alphanumeric string | Ditch
WBS |  | A unique code (work breakdown structure) used to represent a task's position within the hierarchical structure of tasks. | Alphanumeric string separated by periods (.) | PROJ1.Act1.Task.143
Priority |  | Indicates the level of importance assigned to a task. | Alphanumeric string. 1 highest, 99 lowest priority | 77
Milestone |  | Indicates whether a task is a milestone. | True or False - can be 0 for false and 1 for true | False
Summary | Rollup | Indicates whether a task is a summary task. | True or False - can be 0 for false and 1 for true | False
Critical |  | Indicates whether a task has room in the schedule to slip, or if it is on the critical path. | True or False - can be 0 for false and 1 for true | False
Start | StartDate | Date and time that a task is scheduled to begin. | YYYYMMDDTHHMM | 20260602T1230
Finish | EndDate | The date and time that a task is scheduled to be completed. | YYYYMMDDTHHMM | 20260602T1630
Duration |  | Total span of active working time for a task. Not to be confused with the effort required to complete this task. | Alphanumeric string | 4hr
Work | Effort | Total amount of work scheduled to be performed on a task by all assigned resources. | Alphanumeric string | 0.5d
EarlyStart | earliest_start_date | The earliest date that a task can begin, based on the early start dates of predecessor and successor tasks and other constraints. | YYYYMMDDTHHMM | 20260523T0800
EarlyFinish | earliest_end_date | The earliest date that a task can finish, based on early finish dates of predecessor and successor tasks, other constraints. | YYYYMMDDTHHMM | 20260523T1700
LateStart | latest_start_date | The latest date that a task can start without delaying the finish of the project. | YYYYMMDDTHHMM | 20260603T0800
LateFinish | latest_end_date | The latest date that a task can finish without delaying the finish of the project. | YYYYMMDDTHHMM | 20260603T1630
ActualStart |  | Date and time that a task actually began. | YYYYMMDDTHHMM | 20260602T0800
ActualFinish |  | Date and time that a task actually finished. | YYYYMMDDTHHMM | 20260602T1200
Deadline |  | Date entered as a deadline for the task. | YYYYMMDDTHHMM | 20260630
StartVariance |  | The difference between a task's baseline start date and its currently scheduled start date. | Alphanumeric string | -4h
FinishVariance |  | The amount of time that represents the difference between a task's baseline finish date and its current finish date. | Alphanumeric string | -4h
FixedCost |  | A task expense that is not associated with people performing the work - this may be the cost of a fixed price contract, capital acquisition, equipment rental or other non-labor fee. This is the summation of all costs related to this task. | Numeric | 250.00
PercentComplete | percent_complete | The current status of a task, expressed as the percentage of the task's duration that has been completed. | Decimal number between 0 and 1.0 where 1 is 100% | 1.0
PercentWorkComplete |  | The current status of a task, expressed as the percentage of the task's work / effort that has been completed. | Decimal number between 0 and 1.0 where 1 is 100% | 1.0
Cost |  | The total scheduled, or projected, cost for the labor associated with the task. This should exclude any FixedCost items. This is the summation of all labor costs related to this task. | Numeric | 200.00
Notes |  | Notes about the task. | Alphanumeric string | This is the ditch that must be placed 4' from the road for drainage for the water tower.
Resources | resource_names | Names of people associated to this task. | Alphanumeric string | Pete, Garcia
ResourceGroups | resource_groups | Department(s) associated to this task. | Alphanumeric string | Facilities
Predecessors |  | Specifies the predecessor tasks. | ID values or WBS values | 123
Successors |  | Specifies the successor tasks. | ID values or WBS values | 258
Icon |  | Name of icon to be used in visualizations of this task. | Alphanumeric string | shovel
Color |  | Name of the color to be used in visualizations for this task. | Alphanumeric string | Green
Tags |  | Strings associated with this task to be used for selection, filtering, and style rule definition. | Alphanumeric string | Construction, Grounds
Custom1 |  | Custom field holding company / user specific value(s) related to this task to be used for selection, filtering, and style rule definition. | Alphanumeric string | Equipment: $250.00
Custom2 |  | Custom field holding company / user specific value(s) related to this task to be used for selection, filtering, and style rule definition. | Alphanumeric string | Pete: $25/hr Garcia: $25/hr
Custom3 |  | Custom field holding company / user specific value(s) related to this task to be used for selection, filtering, and style rule definition. | Alphanumeric string | CoA: 99345B2026
Custom4 |  | Custom field holding company / user specific value(s) related to this task to be used for selection, filtering, and style rule definition. | Alphanumeric string | Greenbriar Resorts
Custom5 |  | Custom field holding company / user specific value(s) related to this task to be used for selection, filtering, and style rule definition. | Alphanumeric string
Notes
• The only mandatory columns are: Start, Finish, and Name. All other columns are optional.
• Date/time format is YYYYMMDDTHHMM, e.g. 20260704T1230 for 7/4/26 12:30pm. The time part is optional -- 20260704 alone is accepted, as is 20260704T12:30.
• WBS values should be unique across all projects. This can be done easily by including a Project ID as part of the WBS structure.
• Resources and ResourceGroups can contain lists of people's, department and/or company names that are related to tasks. Separate multiple entries with commas.
• There are no length limits to custom fields, notes, and tags. If there are additional fields used in the applications that generate the data, simply concatenate the values from these fields to be able to select, filter, and style visualization data.
• Cost and FixedCost are currency values that are related to labor and non-labor respectively.
• You may want to use one or more custom fields to itemize the costs that were used to derive the FixedCost and Cost fields for each task.
• Duration, Work, StartVariance and FinishVariance accept units: m/min (minutes), h/hr (hours), d (days), w/wk (weeks), mo (months). Examples: 4hr, 0.5d, 2w, 1d 4h, 2w3d, -4h. Note that 'm' means minutes -- use 'mo' for months. A bare number is read as days. Values are converted to decimal days assuming an 8-hour workday, a 5-day week and a 20-day month; the text you type is also kept verbatim.
• Decimal commas and thousands separators are both understood in durations and in Cost / FixedCost. Which character is the decimal point is decided by position, not by locale: a comma followed by exactly three digits groups thousands (1,200 = 1200), otherwise it is a decimal comma (1,5 = 1.5). When both a comma and a period appear, the later one is the decimal point, so 1,234.5 and 1.234,5 both mean 1234.5. The one ambiguous case, 1,500, is read as fifteen hundred -- write 1.5 if you mean one and a half.
• Text that cannot be parsed in a duration or cost cell (n/a, TBD, blank) leaves that one field empty; it never rejects the whole row.
• Delete the three example rows before entering your own data.